## Sheet1
Project Cost Estimates
Project Beginning: 27th March 2020
Project End: 19-26 June 2020
Team members in this time are assumed to be working between 3-5 hours a week on this project. There are 5 members in the group working on the project.
As a result, we expect the total number of hours spent working on the project to be 180 - 300 hours across all team members.
The initial budget for the project is - excluding a backup budget of - which shall only be used to compensate for any issues that may arise during project devleopment that may conist of, but not limited to: employee leave, hardware damage, sudden development changes, health issues etc.
Therefore, the rate for project members is $70/hr.
Release | Iteration | Task | User Story | Process/service | Estimated Hours | Est Cost $70/Hr
Release 1 | Iteration1 | Login to the system | 101 | Access service | 8 | 560
|  | Launch a new application | 201 | Access service | 4 | 210
| Iteration 2 | Save an application | 207 | Application management | 6 | 420
|  | Edit a previously saved application | 401 | Application management | 4 | 280
Iteration 3
Release 2 | Iteration 1
Iteration 2
Iteration 3