## Ueer Story Backlog
Project: | UTS Online Travel Funding (TFA) Approval System
Sponsor(s): | UTS Travel Committee
Version: | 2
Date:
Project ID:
Functional
User Story # | As a/an | I want to... | So that... | Estimates | Priority | Value | NFRs Link to Use Case ID | Status | Release | Iteration | Owner | Process/ Service
101 | Applicant | be able to login with my UTS ID and password | I can access the TFA system. | 1 | H | 10 |  |  | R1 | I1 |  | Login (Applicant)
102 | Applicant | be able to log into the TFA system through my computer | I can attach documents and submit my application for review purposes | 1 | M | 10 |  |  | R1 | I1 |  | Login (Applicant)
103 | Applicant | be able to log into the TFA system through my mobile device | I can attach documents and submit my application for review purposes | 1 | H | 10 |  |  | R1 | I2 |  | Login (Applicant)
201 | Applicant | be able to launch a new application | I can complete a travel funding application | 1 | H | 20 |  |  | R1 | I1 |  | Submit Application
202 | Applicant | be able to have my personal details prepopulated in the application | the travel committee can verify I am eligible to submit a travel funding application | 1 | H | 20 |  |  | R1 | I1 |  | Submit Application
203 | Applicant | be able to electronically enter my travel details | I can specify the details of my travel to the travel committee | 1 | H | 20 |  |  | R1 | I1 |  | Submit Application
204 | Applicant | be able to electronically enter my funding details | I can specify the amount of money I am requesting | 1 | H | 20 |  |  | R1 | I1 |  | Submit Application
205 | Applicant | be able to electronically attach multiple papers to my application | I can support my application to the travel committee | 2 | H | 30 |  |  | R1 | I1 |  | Submit Application
206 | Applicant | be able to submit my application with attached papers online | my application can be reviewed by the travel committee | 3 | H | 40 |  |  | R1 | I1 |  | Submit Application
207 | Applicant | be able to save my application | I can view the application later | 2 | H | 30 |  |  | R1 | I1 |  | Submit Application
208 | Applicant | be able to delete attached documents prior to submission | I can remove incorrect attachments | 1 | L | 10 |  |  | R1 | I1 |  | Submit Application
301 | Applicant | be able to view a list of applications that have been saved | I can see what applications are available for me to view and manage | 1 | M | 10 |  |  | R1 | I2 |  | View Application
302 | Applicant | be able to view an application | I can see if I need to update the application | 1 | H | 20 |  |  | R1 | I2 |  | View Application
303 | Applicant | be able to view the status of a submitted application | I am aware whether my application is pending, has been rejected or accepted | 1 | H | 20 |  |  | R1 | I2 |  | View Application
401 | Applicant | be able to edit the details of a saved application | I can ensure the travel committee has the most current details for my application | 2 | H | 20 |  |  | R1 | I3 |  | Manage Application
402 | Applicant | be able to delete an application | I can remove applications I no longer want to lodge in the system | 1 | L | 20 |  |  | R1 | I3 |  | Manage Application
403 | Applicant | attach additional accepted papers to submitted applications | I can strengthen my application to the travel committee | 1 | L | 20 |  |  | R1 | I3 |  | Manage Application
501 | Committee Member | be able to login with my UTS ID and password | I can access the TFA system. | 2 | H | 10 |  |  | R2 | I4 |  | Login (Committee and Chair)
502 | Committee Member | be able to log into the TFA system through my computer | I can review attached documents and submitted applications for review purposes. | 2 | H | 10 |  |  | R2 | I2 |  | Login (Committee and Chair)
503 | Committee Member | be able to log into the TFA system through my mobile device | I can review attached documents and submitted applications for review purposes. | 2 | M | 10 |  |  | R2 | I2 |  | Login (Committee and Chair)
601 | Committee Member | be able to view a list of applications that have been submitted by applicants | I can select one to review | 1 | M | 20 |  |  | R2 | I2 |  | Review Application
602 | Committee Member | be able to view the application and attached papers | I can make an informed decision about whether the application should be accepted | 3 | M | 30 |  |  | R2 | I2 |  | Review Application
603 | Committee Member | be able to electroniclly indicate whether the application has been approved | travel committee is notified whether application has been accepted | 1 | H | 20 |  |  | R2 | I2 |  | Review Application
604 | Committee Chair | be able to electronically make a final decision regarding an application | an accountable decision is made on travel grants. | 2 | H | 20 |  |  | R2 | I2 |  | Review Application
701 | Committee Member | receive an e-mail notification as soon as an applicant submits a new application | I know that I have an application that requires my decision pending | 2 | H | 20 |  |  | R2 | I3 |  | Email Notification
702 | Applicant | receive an e-mail notification as soon as there is a change to my application status | I know that a decision has been made about my application | 2 | H | 20 |  |  | R2 | I3 |  | Email Notification
801 | System Admin | create a new record | I am able to add a new user | 1 | M | 10 |  |  | R1 | I2 |  | System Admin
802 | System Admin | list a record | I am able to list all users | 1 | M | 10 |  |  | R1 | I2 |  | System Admin
803 | System Admin | view a record | I am able to view the details of a particular user | 1 | M | 10 |  |  | R1 | I3 |  | System Admin
804 | System Admin | update a record | edit the information stored for a particular user | 1 | M | 10 |  |  | R2 | I1 |  | System Admin
805 | System Admin | actitvate a record | initialise a user for the system | 1 | L | 10 |  |  | R2 | I1 |  | System Admin
806 | System Admin | deactivate a record | delete a particular user from the system | 1 | L | 10 |  |  | R2 | I1 |  | System Admin
NFR - Security Requirements
901 | Applicant | ensure my password is masked | I can securely access the travel funding approval system | 1 | H | 10 | 101, 501
902 | Applicant | ensure my personal details are encrypted | I can securely complete registration | 2 | M | 20 | 801
903 | Applicant | ensure that my credentials are encrypted | I can securely log onto the travel funding approval system | 2 | M | 10 | 101, 501
904 | Applicant | be notified whether the system has received input within 5 minutes | I can submit my application | 1 | L | 10 | 203, 204
905 | Applicant | be notified whether the system has received input within 10 minutes | I can submit my application | 2 | L | 10 | 206
906 | Committee Member | ensure my password is masked | I can securely access the travel funding approval system | 2 | H | 10 | 101, 502
907 | Committee Member | ensure my personal details are encrypted | I can securely complete registration | 3 | M | 20 | 802
908 | Committee Member | ensure that my credentials are encrypted | I can securely log onto the travel funding approval system | 3 | M | 10 | 101, 502
909 | Committee Member | be an authorised personnel | I can review an applicant’s application | 2 | M | 20 | 602, 603
910 | Committee Member | be an authorised personnel | I can make a final decision regarding the application | 1 | L | 10 | 702
911 | System Admin | ensure my password is masked | I can securely access the travel funding approval system | 3 | H | 10 | 101, 503
912 | System Admin | ensure my personal details are encrypted | I can securely complete registration | 4 | M | 20 | 803
913 | System Admin | ensure that my credentials are encrypted | I can securely log onto the travel funding approval system | 4 | M | 10 | 101, 503
914 | System Admin | be an authorised personnel | I can remove applications or uses from the database | 2 | L | 10 | 806
NFR - Performance Requirements
1001 | Applicant | login to the system within 5 seconds | I can access my application on the travel funding approval system | 3 | M | 10 | 101, 501
1002 | Applicant | access the travel funding application system on different Internet browsers | I can access my application on the travel funding application system | 2 | L | 10 | N/A
1003 | Applicant | access the TFA system through my computer | I can attach documents and submit my application | 3 | H | 10 | 102
1004 | Applicant | access the TFA system through my mobile device | I can attach documents and submit my application | 3 | M | 10 | 102
1005 | Committee Member | access the travel funding application system on different Internet browsers | I can access an applicant’s application for review and decision making purposes | 2 | L | 10 | N/A
1006 | Committee Member | to be notified of an application 5 seconds after it has been submitted | I can access an applicant’s application for review and decision making purposes | 2 | M | 10 | 303
1007 | Committee Member | login to the system within 5 seconds | I can access an applicant’s application for review and decision making purposes | 3 | M | 10 | 101, 501
1008 | Committee Member | access the TFA system through my computer | I can review submitted applications in order to make a decision | 3 | H | 10 | 502
1009 | Committee Member | access the TFA system through my mobile device | I can review submitted applications in order to make a decision | 3 | M | 10 | 502
1010 | System Admin | ensure that the system can handle 200 concurrent logins | authorised users can access the travel funding approval system | 5 | M | 20 | 101, 501
1011 | System Admin | ensure that the system can handle 200 saved applications and submissions | authorised users can submit their application to the committee for review and decision making purposes | 3 | M | 20 | 206, 207